## general_report
Displaying 7 issues at 4/Jul/17 21:27 PM.
Issue Type | No | Key | Source | Summary | Description | Initial due date | Due Date | Closure date | Status | Progress and details | Responsible | Status
THALES主用 | 1 | 离线参数问题 |  | LES系统备份状态接收IFPL报文检查机型参数 | 当LES备份收到THALES主用发送IFPL报文，对其巡航速度高度依据离线参数文件进行校验，未通过则无法新建FPL | 2017-07-04 |  |  | StartedWork | 莱斯同意与BEST统一AIRCRAFT_PERFORMANCE | LES | open
THALES主用 | 2 | 离线参数问题 |  | LES系统扇区信息与THALES系统不一致 | 因莱斯与THALES扇区信息不一致，移交，CSEC处理，出现异常。 | 2017-07-04 |  |  |  | THALES系统为现场数据，LES不是 | LES | open
THALES主用 | 3 | 系统设置问题 |  | 编组18信息未同步 | THALES传输IFPL报文时将编组18信息拆分，相应的数据项填入对应项中，但TEAM 18项为空，LES必须通过TEAM18获取信息，故现LES备份同步编组18信息为空。 | 2017-07-04 |  |  |  | THALES同意将输出TEAM18数据项 | THALES | open
THALES主用 | 4 | 系统处理问题 |  | ETD时间修改问题 | THALES对已有FPL进行ETD时间修改，eg ETD0755 MOD 0655, LES系统接收处理后又新建一相同航班号，ETD时间为0655的FPL | 2017-07-04 |  |  |  | LES正在调查中 | LES | open
THALES主用 | 5 | 系统处理问题 |  | 编组10A修改机载设备，LES拒收 | THALES修改编组10a项，LES系统同步失败，因LES校验机载设备顺序R必须在W之前 | 2017-07-04 |  |  |  | pending | TBD | open
THALES主用 | 6 | 系统处理问题 |  | LES同步FPL失败，因FPL必须存在入界点 | THALES新建FPL成功，LES因航路信息中无入界点而拒收，再次测试，航路信息为DCT,LES依旧无法同步 | 2017-07-04 |  |  |  | pending | TBD | open
THALES主用 | 7 | 系统处理问题 |  | PRE状态同步问题 | THALES新建FPL成功ETD30min以内，计划处于NACT-PRE状态，并分配SSR，LES接收该计划处于NACT状态，经过CSP:1MIN变为PRE状态，此时LES系统，将THALES分配SSR变为PSSR，之后该飞行计划同步失效 | 2017-07-04 |  |  |  | LES正在调查中 | LES | open
|  |  | dd | dd
TM Action |  | SHH-119 | MoM_008_Status Meeting | SMF-002 feedback on Thales response | SMF-002 feedback on Thales response | 2016-09-02 |  | 2016-09-09 | Closed | Refer email Shen Li -> F. Ferrier 07/09/2016 SMF_SHA_002_rev_002_TR6_response is no forther clarfications |  | EAST ATMB
TM Action |  | SHH-117 | MoM_008_Status Meeting | Confirm HQ maps are OK | Confirm the Hongqiao Autocad map provided by EAST ATMB is OK for dataset preparation | 2016-09-12 |  | 2016-10-19 | Closed | [TR6_DD] 02/11/2016 Mail sent by TR6 integ to BEST with AutoCAD map updated for dataset generation |  | Thales - TR6
TM Action |  | SHH-116 | MoM_006_Status Meeting | ATP feedback | Thales to provide ATP response to EAST ATMB comments | 2016-08-02 | 2016-08-02 | 2016-08-03 | Closed | Refer email 02 August 2016 F.Ferrie -> Shen Li. |  | Thales - TAL
TM Action |  | SHH-115 | MoM_006_Status Meeting | NEHUP PCR status Summary Monthly | Provide a monthly / 2-monthly summary of the NEHUP PCR status, show the correction, dupes and clarification | 2016-08-05 |  | 2016-09-09 | Closed | On-going provision of the monthly GAIA summary to the sites via Jessie PANG |  | BEST
TM Action |  | SHH-114 | MoM_006_Status Meeting | Conduct Site Survey | Thales and BEST to plan conduct of site survey end of July / early August | 2016-08-05 | 2016-11-28 | 2017-02-16 | Closed | BEST Engineer visited site - Changfeng LI 08 September 2016 of the TMA buidling, but due to TMA progress site survey could not be conducted at this time. Planned site survey 21 Nov 2016. [TAL_FF] site survey conducted |  | BEST
TM Action |  | SHH-113 | MoM_006_Status Meeting | Request move of SMF-SHA-007 DCL testing to site acceptance phase | Thales to write formal letter to request SHA-007 DCL in TWR testing to move to site phase | 2016-07-22 | 2016-07-22 | 2016-08-03 | Closed | Refer STMA0101 dated 20 July 2016. Refer email Shen Li -> F. Ferrier 27 July 2016 EAST ATMB agree to move DCL to SAT. |  | Thales - TAL
TM Action |  | SHH-112 | MoM_Shanghai_SDR | Eurocat-TWR FPW Default Tab | SDR MoM STMA_005 Refer to Item#88 Update SMF TWR FPW default tab to be the Route tab | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | TR6 confirms default tab will be the Route tab. There is no SMF to describe this behaviour. |  | Thales - TR6
TM Action |  | SHH-111 | MoM_Shanghai_SDR | Training Schedule Update | SDR MoM STMA_005 Refer to Item#87 Update Training schedule | 2016-03-25 | 2016-03-25 | 2016-03-22 | Closed | Refer to email FF->Shen Li 18 March 2016. Training Summary Schedule Rev003 Refer email Shen Li -> FF 22 March 2016. Rev003 agreed. |  | Thales - TAL
TM Action |  | SHH-110 | MoM_Shanghai_SDR | Update Contract Console Quantities | SDR MoM STMA_005 Refer to Item#86 Update Contract for Console quantities | 2016-03-25 | 2016-04-01 | 2016-04-08 | Closed | Reference STMA0064 Contract variation to Hardware List of Supply Rev002 |  | Thales - TAL
TM Action |  | SHH-109 | MoM_Shanghai_SDR | Update Contract Rack Quantities | SDR MoM STMA_005 Refer to Item#86 Update Contract for Console quantities as per Item#86 | 2016-03-25 | 2016-04-01 | 2016-04-08 | Closed | Refer to STMA0064 Contract Variation to Hardware List of Supply Rev002 |  | Thales - TAL
TM Action |  | SHH-108 | MoM_Shanghai_SDR | Rack Design Update | SDR MoM STMA_005 Refer to Item#83 Update as per Item#83 | 2016-03-25 | 2016-06-30 | 2016-07-18 | Closed | FF 08 April 2016, internal review in progress FF 19 May 2016, internal reviews completed, release required. Refer STMA0099, dated 18/07/2016, Rev002 released to EATMB. |  | BEST
TM Action |  | SHH-105 | MoM_Shanghai_SDR | Rack Location | SDR MoM STMA_005 Refer to Item#81 Provide to BEST the installation (locating in final position) of equipment cabinets, including electrical connectivity within the rack and cabinet grounding | 2016-06-10 | 2016-06-10 | 2016-04-29 | Closed | Refer to email Shen Li -> F. Ferrier 29 April 2016 Rack Layout provided |  | EAST ATMB
TM Action |  | SHH-103 | MoM_Shanghai_SDR | AODB ICD template and AWOS ICD template | SDR MoM STMA_005 Refer to Item#79 Provide AODB ICD template and AWOS ICD template | 2016-04-15 | 2016-04-15 | 2016-04-27 | Closed | Refer email FFerrier->Shen Li 27 April 2016 AWOS and AODB ICD templates sent to EAST ATMB |  | Thales - TR6
TM Action |  | SHH-100 | MoM_Shanghai_SDR | ADS-B and WAM Input Formats | SDR MoM STMA_005 Refer to Item#76 Confirm ADS-B and WAM input formats with the Supplier | 2016-03-25 | 2016-05-27 | 2016-07-29 | Closed | [TAL_FF] refer email LuXuan -> FF 06/07/2016 |  | EAST ATMB
TM Action |  | SHH-94 | MoM_Shanghai_SDR | GSSDD - Location of Servers and Workstations to be Confirmed for HQ and PD | SDR MoM STMA_005 Refer to Item#70 EAST ATMB to provide confirmation of HQ and PD installation configuration prior to Thales-BEST site survey (mid-May) | 2016-05-20 | 2016-05-20 | 2016-04-19 | Closed | STMA Status Meeting @Qingpu 19 April 2016 EAST ATMB confirmed the TWR and HQ configuration: workstations and servers in the equipment room and extend via KVm the display and keyboard to the OPS room, tests confirm configuration is good. |  | EAST ATMB
TM Action |  | SHH-92 | MoM_Shanghai_SDR | Level 2 Tower / MAESTRO Technical and Maintenance & Adaption Data Training in Rungis Date Confirmation | SDR MoM STMA_005 Refer to Item#68 Confirm if Ok to keep dates: 26/09/16 to 21/10/16, or new proposed date 10/10/16 to 4/11/16 | 2016-04-01 | 2016-04-01 | 2016-03-21 | Closed | Refer to SDR Feedback from EAST ATMB 18 March 2016: Keep the original schedule (from 26/09/16 to 21/10/16), and OCT 1th and 2th are day-off (weekend), no more other holiday. |  | EAST ATMB
TM Action |  | SHH-91 | MoM_Shanghai_SDR | Level 2 Tower / MAESTRO Technical and Maintenance & Adaption Data Training in Rungis Dates | SDR MoM STMA_005 Refer to Item#68 TR6 to confirm if move to 10/10/16 to 4/11/16 is OK | 2016-03-25 | 2016-03-25 | 2016-03-21 | Closed | Refer to SDR Feedback from EAST ATMB 18 March 2016. Keep the original schedule (from 26/09/16 to 21/10/16), and OCT 1th and 2th are day-off (weekend), no more other holiday. TR6 confirms Dates agreed by EATMB are finally 26/09/16 - 21/10/16 |  | Thales - TR6
TM Action |  | SHH-90 | MoM_Shanghai_SDR | LOS - Laser Printers | SDR MoM STMA_005 Refer to Item#66 Update the LOS to revert to contract laser printers and quantity | 2016-03-25 | 2016-03-25 | 2016-03-24 | Closed | LOS updated and finalised version forwarded to customer. CDRL_010 rev 2 dated 08 March 16 |  | Thales - TAL
TM Action |  | SHH-88 | MoM_Shanghai_SDR | Eurocat-TWR - SID/STAR menu | SDR MoM STMA_005 Refer to Item#64 Use the list provided by EAST ATMB to configure the SID/STAR menu in user friendly format. Provide a screen shot to EAST ATMB for review | 2016-08-12 | 2016-08-12 | 2016-11-04 | Closed | [TR6_DD] 02/11/2016 Screenshot sent to East ATMB |  | Thales - TR6
TM Action |  | SHH-87 | MoM_Shanghai_SDR | Eurocat-TWR - SID/STAR List Per Runway | SDR MoM STMA_005 Refer to Item#64 EAST ATMB to provide list of SID and STAR per runway | 2016-03-25 | 2016-07-29 | 2016-07-29 | Closed | [TAL_FF]: Can be obtained from current Shanghia OPS dataset. Action to be closed. |  | EAST ATMB
TM Action |  | SHH-86 | MoM_Shanghai_SDR | Eurocat-ATC - ECR 025 - MAESTRO Integration - Departure Runway Management | SDR MoM STMA_005 Refer to Item#63 Update ECR025 as per Item#63 Departure Runway Management | 2016-03-25 | 2016-03-25 | 2016-04-14 | Closed | Refer to STMA0069, document delivery 14 April 2016. |  | Thales - TAL
TM Action |  | SHH-82 | MoM_Shanghai_SDR | Eurocat-TWR - RCMS OS | SDR MoM STMA_005 Refer to Item#52 confirm during Factory integration if can use Thalix for Eurocat-TWR RCMS. | 2016-06-06 | 2016-08-26 | 2016-11-04 | Closed | [TAL_FF] 29/07/2016 testing in progress [TR6_DD] 02/11/2016 RMCS delivered in Thalix for FAT |  | Thales - TR6
TM Action |  | SHH-81 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] DCL Free text | SDR MoM STMA_005 Refer to Item#51 Update SMF-SHA-007 [DCL] DCL Free text as per Item#51 | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | Rev002 of SMF delivered 01/04/2016 |  | Thales - TR6
TM Action |  | SHH-80 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_024 [Display Callsign and SSR on uncoupled Mode-S tracks] update | SDR MoM STMA_005 Refer to Item#48 Update ATC ECR_024 [Display Callsign and SSR on uncoupled Mode-S tracks] to enabled or disabled off-line | 2016-03-25 | 2016-03-25 | 2016-03-21 | Closed | Refer to STMA_0054 dated 10 March 2016. Revised ECR delivered post SDR discussions. |  | Thales - TAL
TM Action |  | SHH-79 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_023 [MTCD Function] Offline Definable Not Raise Alerts for Uncoupled tracks | SDR MoM STMA_005 Refer to Item#46 Update ATC ECR_023 [MTCD Function] not raise alerts for uncoupled tracks. Will be off-line defined. | 2016-03-25 | 2016-03-25 | 2016-07-29 | Closed | Refer to STMA0075, 03/05/2016, ECR_23 Rev002 approved. |  | Thales - TAL
TM Action |  | SHH-78 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_023 [MTCD Function] BRL Function | SDR MoM STMA_005 Refer to Item#45 Update ATC ECR_023 [MTCD Function] BRL clarification | 2016-03-25 | 2016-03-25 | 2016-05-03 | Closed | Refer to STMA0075, document delivery. ECR_25 approved. |  | Thales - TAL
TM Action |  | SHH-77 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_018 [Monitor Eurocat-TWR from TMA] to be Removed | SDR MoM STMA_005 Refer to Item#40 Remove ATC ECR_018 [Monitor Eurocat-TWR from TMA] | 2016-03-25 | 2016-03-25 | 2016-05-19 | Closed | ECR set to dna. The additional RCMS position will be moved to the ACC. |  | Thales - TAL
TM Action |  | SHH-76 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_011 [SID/STAR name up to 11 characters] | SDR MoM STMA_005 Refer to Item#34 Update ATC ECR_011 [SID/STAR name up to 11 characters]to describe more detail, SID/STAR edit | 2016-03-11 | 2016-03-11 | 2016-03-10 | Closed | Refer to STMA_0053 Revised ECR delivered post SDR discussions. |  | Thales - TAL
TM Action |  | SHH-75 | MoM_Shanghai_SDR | Eurocat-ATC - ECR_06 [Back-up Mode] | SDR MoM STMA_005 Refer to Item#29 confirm if Thales proposed architecture change is acceptable Refer to STMA0088 01/06/2016 ECR_06 Rev003 Approved. | 2016-03-25 | 2016-06-01 | 2016-06-01 | Closed | EATMB confirmed that during the transition time the backup system shall have a capability to stop the consistency between 2 systems. For the architecture changing propose, EATMB prefer to “agree”, currently BEST and I28 are under discussion for finalization. Thales: ECR 6 will be updated to introduce a new Standalone Backup mode which is identical to Backup mode without listening for consistency messages from the Main system |  | EAST ATMB
TM Action |  | SHH-74 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-009 [Coupling Improvement] Automatic Correlation for Dep FPL Feedback | SDR MoM STMA_005 Refer to Item#17 Provide feedback on Thales explanation on SMF-SHA-009 [Coupling Improvement] Automatic Correlation for Dep FPL Feedback | 2016-04-08 | 2016-05-09 | 2016-05-09 | Closed | Refer email Shen Li-> F.Ferrier 09 May 2016 |  | EAST ATMB
TM Action |  | SHH-73 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-009 [Coupling Improvement] Explaination of SSR Code Not Used for Automatic Correlation for Dep FPL | SDR MoM STMA_005 Refer to Item#17 Provide detailed reason why (technical and operational) SSR code is not used. Explanation to consider MLAT and ADSB | 2016-03-21 | 2016-04-01 | 2016-04-15 | Closed | SSR added to criteria for coupling of departure flights Refer STMA0070, Rev003 delivered. |  | Thales - TR6
TM Action |  | SHH-72 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-009 [Coupling Improvement] Codes Update | SDR MoM STMA_005 Refer to Item#17 Update SMF-SHA-009 [Coupling Improvement], codes: 3000, 4000, 5000, 6000, 7000 can be used | 2016-03-25 | 2016-05-27 | 2016-07-29 | Closed | Rev002 of SMF delivered, reference STMA0062 Rev003 of SMF delivered, reference STMA0070, 19 May 2016 Thales reviewing comments from EAST ATMB. Refer to STMA0097, 08 July 2016, SHA-009 Rev003 Approved |  | Thales - TR6
TM Action |  | SHH-71 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] Current State Menu | SDR MoM STMA_005 Refer to Item#15 Update SMF-SHA-007 [DCL] Current State Menu as per item #15 | 2016-03-25 | 2016-04-01 | 2016-04-07 | Closed | Rev002 of SMF delivered , reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-70 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] Display the Inconsistency With Highlight | SDR MoM STMA_005 Refer to Item#15 Update SMF-SHA-007 [DCL] to display the inconsistency on the DCL window by a highlight colour | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | Rev002 of SMF delivered, reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-69 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] free text field | SDR MoM STMA_005 Refer to Item#15 Update SMF-SHA-007 [DCL] In case of runway change, the free text field will be updated accordingly | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | Rev002 of SMF delivered, reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-68 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] Frequency List | SDR MoM STMA_005 Refer to Item# Update SMF-SHA-007 [DCL] frequency list as per item #15 | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | Rev002 of SMF delivered, reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-67 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-007 [DCL] one altitude per runway | SDR MoM STMA_005 Refer to Item#15 Update SMF-SHA-007 [DCL] with one altitude per runway (ie per runway direction) | 2016-03-25 | 2016-04-01 | 2016-04-01 | Closed | Rev002 of SMF delivered, reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-65 | MoM_Shanghai_SDR | Eurocat-TWR - SMF-SHA-002 [Interface AWOS/D-ATIS] Format | SDR MoM STMA_005 Refer to Item#10 Update SMF-SHA-002 [Interface AWOS/D-ATIS] with proposed format | 2016-03-25 | 2016-08-26 | 2016-11-02 | Closed | Clarifications response from EAST ATMB received 07/04/2016. Update of the SMF is in progress. 19 May 2016. Internal review in progress 07 Oct. 2016 Refer to STMA0115, SMF-SHA-002_rev002.pdf approved 7 July 2016 Comments received from EAST ATMB for SMF-002 Rev002. 19 July 2016 Tranlated comments sent to TR6 for review. |  | Thales - TR6
TM Action |  | SHH-64 | MoM_Shanghai_SDR | Eurocat-TWR - Syllabus to Include Areas Changes can be Managed by EAST ATMB | SDR MoM STMA_005 Refer to Item#7 Include in Data Adaptation Training syllabus topics can focus on areas which can be managed by EAST ATMB without Thales assistance | 2016-09-05 | 2016-12-23 | 2017-02-27 | Closed | [TR6_DD] 02/11/2016 Included in Data Adaptation training [TAL_FF] 27/02/2017 Refer to STMA0138, Data Adaptation training materials Rev002. This action is closed and tracking will be monitored in SHH-127 Additional information is to be summarised and documented in SMM. |  | Thales - TR6
TM Action |  | SHH-61 | MoM_Shanghai_SDR | Eurocat-TWR - EFS Configuration Examples | SDR MoM STMA_005 Refer to Item#7 Provide EFS configuration examples, layout criteria and recommended work procedures | 2016-04-15 | 2016-06-03 | 2016-05-30 | Closed | Takes into account action SHH-60 19 May 2016 Internal review in progress 30 May 2016 Refer to STMA0087, Eurocat – TWR Flight Sorting Criteria and EFS Configuration Examples |  | Thales - TR6
TM Action |  | SHH-60 | MoM_Shanghai_SDR | Eurocat-TWR - EFS Flight Sorting Criteria | SDR MoM STMA_005 Refer to Item#5 Add a criteria on Departure Clearance Given flag. On selection of the sorting criteria, strips contained in the flight list will be re-ordered. | 2016-03-25 | 2016-06-03 | 2016-05-30 | Closed | Confirmed. This will be included in the document provided as part as action SHH-61 refer to STMA0087 dated 30 May 2016 Eurocat – TWR Flight Sorting Criteria and EFS Configuration Examples |  | Thales - TR6
TM Action |  | SHH-59 | MoM_Shanghai_SDR | Eurocat-TWR - DCL in EFS | SDR MoM STMA_005 Refer to Item#4 Update SMF to show the correct DCL position and workflow | 2016-03-25 | 2016-04-01 | 2016-04-04 | Closed | Rev002 of SMF-SHA-007 delivered, reference STMA0062 |  | Thales - TR6
TM Action |  | SHH-58 | MoM_Shanghai_SDR | Eurocat-TWR - Data Analyser Tool to be included in Rungis Training | SDR MoM STMA_005 Refer to Item# Data Analyser Tool to be included into Rungis Data Adaption Training syllabus | 2016-12-01 | 2016-12-23 | 2017-02-27 | Closed | [TR6_DD] 02/11/2016 Included in Data Adaptation training [TAL_FF] 27/02/2017 Refer to STMA0138, Data Adaptation Training materials Rev002 |  | Thales - TR6
TM Action |  | SHH-57 | MoM_Shanghai_SDR | Eurocat-TWR - Data Analyser Tool OH | SDR MoM STMA_005 Refer to Item#3 Prepare Data Analyser Tool OH for STMA, release 1 month prior to Rungis Data Adaption Training | 2016-08-01 | 2016-08-26 | 2016-11-04 | Closed | [TR6_DD] 02/11/2016 Delivered refer to STMA0118 27 Oct 2016 |  | Thales - TR6
TM Action |  | SHH-56 | MoM_Shanghai_SDR | Eurocat-TWR - Closed Runway Incursion Conflict Detection | SDR MoM STMA_005 Refer to Item#2 Closed runway incursion conflict detection. Provide this feedback to the Eurocat-TWR Product team | 2016-03-18 | 2016-03-18 | 2016-03-18 | Closed | Request described to Eurocat Tower product team. Evolution is not planned so far. |  | Thales - TR6
TM Action |  | SHH-55 | Status_17Dec2015 MoM | Letter of invitation details | Thales will send to EAST ATMB the required details to complete for input to the letter of invitation letters | 2016-01-08 | 2016-01-08 | 2016-02-04 | Closed | Conversation 08/01/2016 F. Ferrier and Shen Li Approval process requires: letter of invitation for overseas travel, date and syllabus are required from Thales to support EAST ATMB to obtain: (1) Team approval (2) Individual approval (with names) Letter of invitation is required from Thales for Visa approval with the individual names. F.Ferrier 18/01/2016 (refer STMA_023, 024, 025, 026, 027 & 028) Letter of Invitations submitted for all overseas training. SDR LOI complete - reference STMA0042 dated 02 Feb. 2016 |  | Thales - TAL
TM Action |  | SHH-54 | Status_17Dec2015 MoM | Customs and Quarantine documentation application for approval to declare as system - time Sequence | Send time sequence and dependent actions leading to submission of the required documentation for shipping as system and to seek approval from Pudong quarantine exemption of some HW without CCC | 2016-01-08 | 2016-01-08 | 2016-01-18 | Closed | Refer email F. Ferrier => Shen Li 18/12/2015 |  | Thales - TAL
TM Action |  | SHH-53 | Status_17Dec2015 MoM | Control & Monitoring options for OASYS Problem | Present possible control & monitoring options for OASYS problem at SDR | 2016-02-05 | 2016-02-05 | 2016-03-11 | Closed | Refer STMA0035 dated 21 Jan. 2016 Control & Monitoring Options for OASYS Problem 04 Feb 2016 - EAST ATMB feedback Thales to provide response/clarification on RCMS Refer STMA0055, MOM_005 SDR |  | Thales - TAL
TM Action |  | SHH-52 | Status_17Dec2015 MoM | Provide NEUP_NEHUP FBL and all NEHUP ICDs | Provide NEUP_NEHUP FBL and all NEHUP ICDs | 2016-01-15 | 2016-01-15 | 2016-01-18 | Closed | Refer email F. Ferrier to Shen Li 18/01/2016 NEUP_NEHUP FBL submitted. |  | Thales - TAL
TM Action |  | SHH-51 | Batch 1 Workshop MoM | Maximum number of active NTZ areas | The maximum number of active NTZ areas is limited to 1 active NTZ area per runway pair, up to a maximum of 12 (as per the capacity increases at Section 8.2 of Nego MoM). The following actions will be carried out: (1) A doc PCR to update the NEHUP SSS to match the software behaviour (1 active NTZ area per runway pair); and (2) We will also update the STMA ECR_07 Capacity Increases to add the limit of 12 active NTZ areas. | 2016-01-22 | 2016-01-22 | 2016-01-08 | Closed | Update of ECR 7 started as per Batch 1 clarifications. STMA_ECR_07_Rev002 approved dated 08/01/2016 |  | Thales - TAL
TM Action |  | SHH-50 | Batch 1 Workshop MoM | Update of ECR 17 | EAST ATMB: Suggested to keep the current GIW1 and GIW2 layout, if the system and position mode changed, then highlight the GIW2 button at GIW1 window. Thales: Agree to keep current layout. Highlight the GIW2 button and the user can click on the highlight to obtain more information on GIW2 Thales will update ECR17 and release before SDR for final review. | 2016-01-22 | 2016-01-22 | 2016-01-08 | Closed | ECR 17 update started as per Batch 1 clarifications. STMA_ECR_17_Rev002 approved dated 08/01/2016 |  | Thales - TAL
TM Action |  | SHH-49 | Batch 1 Workshop MoM | VR audio file transfer ICD | EAST ATMB: The supplier for Shanghai TMA Voice Recorder and Replayer has not been selected yet. The capability to provide audio file (WAV or MP3) should be possible. No corresponding ICD is defined. EAST ATMB requests Thales to provide an Voice Recorder audio file transfer ICD for EAST ATMB to use in their discussions with the Supplier to provide this capability. Thales to provide VR audio file transfer ICD | 2015-12-11 | 2015-12-11 | 2015-12-17 | Closed | Delays in acquiring the VR audio file transfer ICD, still in progress Refer to MoM_003 dated 17 Dec 2015. Agree to use the NEHUP Voice Replayer ICD at TMA |  | Thales - TAL
TM Action |  | SHH-48 | Clarification | STMA FBL - Non Impacted ICDs | Refer to email Shen Li-> Fay Ferrier 10 Dec 2015. Clarified with EAST ATMB and agreed that for NEUP/NEHUP ICDs not impacted by STMA ECRs, no need to modify. Action for Thales to provide list of non-impacted NEUP/NEHP ICDs for EAST ATMB to. Clarification request details below: (1) For those ICDs which are impacted by ECRs, the ICD will be modified accordingly (2) For those ICDs which are not impacted by ECRs, I would like to request and confirm with you that there is no need to modify (as no changes needed), the reference baseline and is agreed is the NEUP & NEHUP FBL and can be referred to as such (reference Technical Spec page 20) There are 24 ICDs which falls into this category – no impact from ECRs. | 2015-12-24 | 2015-12-24 | 2016-01-18 | Closed | F.Ferrier 18/01/2016 Refer to SHH_52 NEUP_NEHUP FBL. ICDs information included in SHH_52. |  | Thales - TAL
TM Action |  | SHH-43 | MoM_Shanghai_TMA_KOM | Investigate New ECR to Replace ECR_ATC_13 | Reference discussion item #29 EAST ATMB requested display target ID and SSR code in the label for uncoupled Mode-S tracks. Thales will investigate and advise the possibility of this change. | 2015-12-11 | 2015-12-11 | 2015-11-27 | Closed | Email 24 Nov 2015 Fay Ferrier -> Shen Li, Proposal sent to E-ATMB to choose replacement ECR. Response 27 Nov 2015 Shen Li -> Fay Ferrier, EAST ATMB confirmed ECR as requested at KOM: to display target ID and SSR code in the label for uncoupled Mode-S tracks |  | Thales - TAL
TM Action |  | SHH-42 | MoM_Shanghai_TMA_KOM | Shipping Solution | Reference Action #26 and discussion item #8 Thales/CASITC/BEST to brain storm and resolve the shipping issue / risk. | 2016-03-25 | 2016-03-25 | 2016-04-04 | Closed | refer email Jessie Pang->Fay Ferrier 14/12/2015 Spoke with Mr. SHEN, director of department which in charge of set of equipment importation of PuDong Quarantine Office. They said in order for them to make decision on whether it is consider as set of equipment, we shall present: 1. Contract 2. End-user Letter, to stating the situation and introduction of the system 3. Thales/CASITC letter, to stating the situation and introduction of the system So, if they consider it is set of computer, then it will not require all CCC certificate, but we still need to provide all the CCC that we have. I have informed CASITC Mr. YANG Bin, the person who in charge of this program. He will report to Mr. SHEN accordingly and see what action they will take. Fay Ferrier 16/12/2015 Thales with BEST - preparation of CCCs and letters in planning phase. Koop 04/04/16 Shipping process finalised including altered shipments IAW with CVP. Preperation of CCC documentation and other paperwork covered inder SHH-23. Action closed. |  | Thales - TAL
TM Action |  | SHH-41 | MoM_Shanghai_TMA_KOM | Shipping Risk | Reference Action #26 and discussion item #8 Thales and EAST ATMB to track the shipping risk until resolved. Risk to be tracked in quarterly Project Status Reporting. | 2015-12-23 | 2015-12-23 | 2015-12-16 | Closed | Refer to PSR Dec 2015 |  | Thales - TAL
TM Action |  | SHH-40 | MoM_Shanghai_TMA_KOM | New Training Format | Reference Action #25 Provide response to the new training format requested by EAST ATMB | 2015-12-11 | 2015-12-11 | 2015-12-09 | Closed | Thales confirms the requested new format training can be accommodated: TR#2 Tower / MAESTRO Controller Instructor, consisting of: - Course (a) Eurocat-TWR Controller and MAESTRO DMAN Controller Instructor Training Conduct Schedule: Mon 29/08/16 - Fri 16/09/16 - Course (b) MAESTRO AMAN/DMAN Controller Instructor Training. Conduct Schedule: Mon 29/08/16 - Fri 16/09/16 TR#4. Level 2 Tower / MAESTRO Technical and Maintenance Conduct Schedule: Mon 26/09/16 – Fri 28/10/16 TR#6. Adaption Data Training Conduct Schedule: Mon 26/09/16 – Fri 28/10/16 Refer to Training Schedule for more details in STMA0012 |  | Thales - TAL
TM Action |  | SHH-39 | MoM_Shanghai_TMA_KOM | Update High Level Training Schedule | Reference Action #24 Update the training high level schedule presented at KOM to reflect moving Melbourne technical training to occur as early as possible. | 2015-11-27 | 2015-11-27 | 2015-12-10 | Closed | Refer to updated high level training schedule in letter correspondence STMA0009. |  | Thales - TAL
TM Action |  | SHH-38 | MoM_Shanghai_TMA_KOM | System Expert Resume Questions | Reference Action #23 Provide resume questions to assist System Experts profiles for EAST ATMB to complete. | 2015-11-27 | 2015-11-27 | 2015-11-27 | Closed | Refer STMA0009 KOM Actions Response
TM Action |  | SHH-37 | MoM_Shanghai_TMA_KOM | Common Thalix Version | Reference Action #22 Thales to provide analysis and response to request from EAST ATMB to have common Thalix version for TMA/ACC/TWR | 2015-12-11 | 2015-12-11 | 2015-12-08 | Closed | Thales confirms Z420 and DL380 G8 will be able to run Thalix 11.1 and supported. Thales will create new action to provide the testing information and recommended upgrade process at SDR. |  | Thales - TAL
TM Action |  | SHH-35 | MoM_Shanghai_TMA_KOM | Draft Contract Variation for HW Model Changes | Reference Action #20 Draft contract variation to EAST ATMB in Dec 2015 to document the changes in hardware models for formal sign off in January 2016 | 2015-12-18 | 2016-04-01 | 2016-04-08 | Closed | 10/02/2016 F.Ferrier LOS reviewed with EAST ATMB 05/02/2016, additional request for 2Kx2K compatibility kits. Thales to confirm the price and conduct a further review with EAST ATMB to make adjustments to HW quantities to offset new requirements for 2Kx2K compatibility kits FF 08 April 2016 reference STMA0065 delivery of STMA LOS Rev002 approved |  | Thales - TAL
TM Action |  | SHH-34 | MoM_Shanghai_TMA_KOM | Server and Workstation Configurations | Reference Action #19 Thales to provide exact server and workstation configurations. | 2015-11-20 | 2015-12-11 | 2015-12-15 | Closed | HP server and workstation configurations attached. Reference STMA0013 |  | Thales - TAL
TM Action |  | SHH-33 | MoM_Shanghai_TMA_KOM | Combined AWOS/ATIS ICD | Reference Action #18 EAST ATMB to provide combined AWOS/ATIS ICD. | 2015-11-20 | 2015-11-20 | 2015-11-16 | Closed | Refer email Shen Li -> Fay Ferrier 12 Nov 2015. Translation Hao Jiasheng 16 Nov 2015 |  | EAST ATMB
TM Action |  | SHH-32 | MoM_Shanghai_TMA_KOM | FAT Test Topics for TWR and MAESTRO | Reference Action #17 Thales to provide a list of test topics for FAT for Eurocat-TWR and MAESTRO AMAN/DMAN. List to be provided for SDR. | 2016-01-28 | 2016-01-28 | 2016-02-05 | Closed | Refer to STMA_ATP_Rev001 , delivered at STMA0046 dated 05/02/2016 |  | Thales - TR6
TM Action |  | SHH-31 | MoM_Shanghai_TMA_KOM | ECP_ATC_23 - Reduce FPCF Look Ahead Time - Use case Scenarios | Reference Action #16 Provide Use Case scenarios to be included in the ECR. ECR workshop will discuss the appropriate use of Thales proposal to meet user needs. | 2016-01-05 | 2016-01-05 | 2016-02-04 | Closed | Operational scenario preparation started. FPCF demo workshop conducted at Qingpu ACC (18 - 19 Jan 2016) by BEST AOS. Outcome of workshop is clarified requirements for MTCD function. |  | Thales - TAL
TM Action |  | SHH-30 | MoM_Shanghai_TMA_KOM | ECP_ATC_15 - PBN Display Clarification | Reference discussion item #16 EAST ATMB currently both ACC and APP use RNAV, but in the future APP should use RNP. Thales proposes to have priority order off-line defined in order to avoid any future changes. To be defined in POSITION_SETTINGS. ECR design as per discussion. | 2015-11-27 | 2015-11-27 | 2015-11-30 | Closed | ECR written in line with KOM discussion and delivered in ECR Batch 2. |  | Thales - TAL
TM Action |  | SHH-29 | MoM_Shanghai_TMA_KOM | ECP_ATC_14 - Callsign Mismatch Highlight - clarification | Reference Action #15 EAST ATMB confirmed: - callsign highlight required is different colour (not red) - highest priority is Mode-S callsign mismatch highlight first then SSR mismatch highlight ECR design as per discussion. | 2016-01-05 | 2016-01-05 | 2016-02-10 | Closed | ECR_STMA_14 - Callsign Mismatch released in ECR batch #4, in line with KOM clarifications. |  | Thales - TAL
TM Action |  | SHH-28 | MoM_Shanghai_TMA_KOM | ECP_ATC_13 - Alert of Non-reception of AFTN Messages - ECR drop | Reference Action #14 Thales advised it is possible to send the alert to OASYS as initially requested by EAST ATMB. EAST ATMB agreed the alert can be displayed in OASYS not the MMI Error message as per the Contract MoM Nego 2.1 and advised the function is already in current version and DPR files have been modified for use. The ECR is to be dropped. | 2015-11-22 | 2015-11-22 | 2015-12-07 | Closed | Agreed to drop during Kick-off meeting. |  | Thales - TAL
TM Action |  | SHH-27 | MoM_Shanghai_TMA_KOM | ECP_ATC_11 - Increase SID/STAR Length clarification | Reference Action #13 EAST ATMB confirmed the following display format: Up to 7 characters will be display in full, if more than 7 display with "+" ECR design as per discussion. | 2015-11-16 | 2015-11-16 | 2015-11-24 | Closed | ECR 11 writing completed and in line with KOM clarifications. ECR 11 submitted to E-ATMB for review 16/11/2015. |  | Thales - TAL
TM Action |  | SHH-26 | MoM_Shanghai_TMA_KOM | ECP_ATC_10 - FDO Message Filter - FDO queues keywords search | Reference Action #12 EAST ATMB Requires the functionality to be able to search the FDO queues based on keywords matching message time, callsign etc. Confirmed the quantity of 100 keywords is not required, the window layout and number of keywords including ability to search on several keywords will be defined during the workshops. | 2016-01-05 | 2016-01-05 | 2015-12-15 | Closed | ECR 10 delivered, reference STMA0010
TM Action |  | SHH-25 | MoM_Shanghai_TMA_KOM | ECP_ATC_9 DUPE Processing Improvement - Distance Check | Reference Action #11 The new distance check should be separate i.e even if the tracks are not eligible for a DUPE alert with current NEHUP software, they can be eligible with the new criteria. The typical scenario is two coupled tracks with the same SSR. As both are coupled, they will not normally generate a DUPE alert, but with the new check, if they come under the off-line defined distance of each other, a DUPE shall be raised. ECR design as per the discussion. | 2015-12-24 | 2015-12-24 | 2015-12-15 | Closed | ECR 09 delivered, reference STMA0014 |  | Thales - TAL
TM Action |  | SHH-24 | MoM_Shanghai_TMA_KOM | ECP_ATC_5 - ATFM Enhancement - ECR description | Reference Action #10 The ECR description shall contain the ADEXP message processing and message sequence examples | 2016-01-15 | 2016-01-15 | 2015-12-15 | Closed | ECR 5 delivered, reference STMA0014 |  | Thales - TAL
TM Action |  | SHH-22 | MoM_Shanghai_TMA_KOM | SDR Letter of Invitation | Reference Action #7 EAST ATMB to advise when SDR Letter of Invitation required. Thales to provide SDR Letter of Invitation | 2015-12-31 | 2015-12-31 | 2016-02-08 | Closed | Reference STMA0042 |  | EAST ATMB
TM Action |  | SHH-21 | MoM_Shanghai_TMA_KOM | WAM Output Format | Reference Action 8. EAST ATMB to confirm WAM output format, if it is possible for both CAT 109/020 and 021. | 2015-11-20 | 2015-11-20 | 2015-11-12 | Closed | Reference email Shen Li -> Fay Ferrier 12 Nov 2015. Target Processors in the MLAT system(also WAM), both of them send Asterix outputs at the same time. Each Target Processor can have configurable amount of output channels. Each output channel can be set to different Asterix Category, IP address & Port, the end-user is able to change IP addresses & Ports in Management system any time if they want. for example: Channel 1 : AST CAT 19 Channel 2 : AST CAT 20 Channel 3 : AST CAT 19 + AST CAT 20 Channel 4 : AST CAT 21 |  | EAST ATMB
TM Action |  | SHH-20 | MoM_Shanghai_TMA_KOM | SDR date in Master Schedule | Reference Action #6 Update the SDR date in the master schedule to start 2 weeks after the Chinese New Year (29 Feb 2016). | 2015-12-24 | 2015-12-24 | 2015-12-16 | Closed | Refer to Master Schedule in PSR (18 Dec 2015). |  | Thales - TAL
TM Action |  | SHH-19 | MoM_Shanghai_TMA_KoM | Review SDR Delay | Reference Action #4 and #5 EAST ATMB advised that approval from CAAC required prior to visa application. There is a risk that the approval process may take longer than expected and the SDR would need to be postponed or another possibility is to conduct SDR in Shanghai. Action is for Thales to review: (1) Impact of SDR delay (2) If SDR can be conducted in Shanghai | 2015-11-27 | 2015-11-27 | 2015-11-25 | Closed | The delay of SDR conduct beyond current agreed date of 29 Feb 2016 will impact baselining the design and the start date for software development. This will also have an effect on readiness for FAT. Thales recommends not to delay the SDR beyond 29th Feb 2016. If EAST ATMB advises the travel to SDR in Melbourne is not approved, then it is possible for Thales, TR6 and BEST to travel to Shanghai to conduct the SDR. |  | Thales - TAL
TM Action |  | SHH-18 | MoM_Shanghai_TMA_KOM | Cable Plan for TMA Technical/Equipment Room | EAST ATMB to provide cable plan for the TMA Technical/Equipment room for Thales review prior to SDR. | 2016-02-05 | 2016-08-26 | 2016-09-09 | Closed | Refer email Shen Li -> F. Ferrier 11 Aug 2016 cable plan provided. |  | EAST ATMB
TM Action |  | SHH-17 | MoM_Shanghai_TMA_KOM | SSF Point of Contact | Provide SSF point of contact prior to SSF installation works. | 2016-11-01 | 2016-11-01 | 2015-12-08 | Closed | Refer email Shen Li -> Fay Ferrier 08/12/2015 EAST ATMB has informed Mr.He ziyue and Mr.Han zhennian about the the SSF additional device for Shanghai TMA project, and they will work with BEST to figure out how to install these device |  | EAST ATMB
TM Action |  | SHH-16 | MoM_Shanghai_TMA_KOM | Autocad of Building Layout - TMA OPS Room | EAST ATMB to provide autocad format of builing layout for TMA OPS Room | 2015-12-31 | 2016-08-31 | 2016-08-08 | Closed | [TAL_FF] Rack locations provided. Confirm the layout of the TMA OPS. [TAL_FF] Status meeting 08/08/2016 between Shen Li/Jiasheng/F.Ferrier - agreed the TMA OPS layout is not required. Action can be closed. |  | EAST ATMB
TM Action |  | SHH-15 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | D-ATIS Interface (Customer) | D-ATIS Interface Contract Neg_2.14 Thales: this interface was not listed in the RFT Agreed Resolution: East ATMB shall collect and assemble AWOS and D-ATIS information together to be sent to the Eurocat-TWR system using the planned AWOS Serial interface. Thales shall propose a format for this interface in order to finalise the interface design. Thales confirms that the D-ATIS version letter (when received) will then be displayed in the DCL window. | 2016-02-22 | 2015-11-16 | 2015-11-16 | Closed | Reference email Shen Li -> Fay Ferrier 12 Nov 2015 Combined AWOS and ATIS ICD provided. |  | EAST ATMB
TM Action |  | SHH-14 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | TWR Radar positions | MoM Reference 5.19 • East ATMB questions why there are 2 screens for ATC Radar position in TWR. • Thales proposes to remove the Auxiliary screen on all Eurocat-ATC positions in the towers. Agreed Resolution: Both parties agreed to remove the Auxiliary screen on all Eurocat-ATC positions in the towers. | 2015-07-10 | 2015-07-10 | 2015-07-07 | Closed | Refer to Contract System Technical Specification RevA. Pudong and Hongqiao TWRs AD updated. |  | Thales - TAL
TM Action |  | SHH-13 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | TMA Bypass Function | MoM Reference 5.17 • RTP and ADSB-FP on one node, MSTP and SNMAP on one node | 2016-01-22 | 2016-01-22 | 2016-02-18 | Closed | Update will be provided in SSDD Refer STMA0048, SSDD Rev001 delivery |  | Thales - TAL
TM Action |  | SHH-12 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | CISCO Switches - RFT Clause 2.5.7 and 2.5.7.2 | MoM Reference 5.14 • East ATMB states the switch model CISCO 4510 should be replaced by 4506 (dual power supply) • Thales agrees with the proposal. | 2015-12-24 | 2015-12-24 | 2016-01-29 | Closed | LOS in progress Refer to STMA_LOS_Rev001, delivered at STMA0036 dated 29/02/2016 |  | Thales - TAL
TM Action |  | SHH-11 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | Smooth transition of Radar Mode on HMI | MoM Reference 5.7 • East ATMB request for a smooth transition (i.e. tracks display continuity) from Main to Bypass. • Thales: Pending. Not currently in proposal. Agreed Resolution: Thales shall import this functionality, done on NESACC. In order to ensure: • Norm -> Mono: Smooth transition (as the mono-radar track is used to build the multi-radar track) | 2016-06-01 | 2015-12-23 | 2015-12-15 | Closed | ECR_21 delivered, reference STMA0014 |  | Thales - TAL
TM Action |  | SHH-10 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | HW Servers Configuration | MoM Reference 5.4 Agreed Resolution: In order to facilitate maintenance procedure between ACC and TMA, the server model to be delivered shall be HP DL380. | 2015-10-29 | 2015-10-29 | 2015-12-08 | Closed | Thales confirms the server model will be HP DL380 G9. This action is now superseded by SHH-34 - Server and Workstation Configurations. |  | Thales - TAL
TM Action |  | SHH-8 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | Traffic Management Fix List Increase | MoM Reference 3.17 • East ATMB requested to have the number of fixes in System Fix List Window to be increased to 200, to be displayed in separated sections and fix per section should be configurable. • Thales states that it’s an out of scope request but will analyse Agreed Resolution: Thales shall implement this ECR in the frame of Shanghai TMA project. High level description: The number of fixes in Traffic Management System Fix List Window to be increased from 100 to 200 and to have the fixes in the System Fix List Window displayed in separated sections | 2017-08-01 | 2017-08-01 | 2015-11-30 | Closed | Related changes captured in ECR_ATC_16 - Traffic Management Fix List Increase, delivered in ECR Batch 2. |  | Thales - TAL
TM Action |  | SHH-7 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | Recording and Replay in the ACC - RFT Clause 2.2.3.10 | MoM Reference 3.8 Agreed Resolution: Thales shall deliver EHMIR at the ACC. This requires software deployment and integration. The number of days of storage shall be limited to 10 days in order to keep the current disk size implemented for NEHUP (500GB). 1 EHMIR license shall be provided to East-ATMB | 2015-05-08 | 2015-12-23 | 2016-08-03 | Closed | East-ATMB to confirm which position should have the EHMIR license in the ACC. Reference email Shen Li-> Fay Ferrier 10 Dec 2015 ACC EHMIR position we plan to set at OPSUP Refer to SDR MoM_005 Discussion Item#44 Action is closed. ECR_22 will be tracked as per the normal ECR approval process. |  | Thales - TAL
TM Action |  | SHH-6 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | DCL Function – RFT Clause | MoM Reference 3.4 Agreed Resolution: Eurocat-TWR to handle the DCL interface in Pudong and Hongqiao. Only the standard ED85A is to be supported and this interface is to be provided by ATMB. No PDC functionality is required. Thales confirms that the Eurocat-TWR positions in the towers can be reconfigured to activate the Eurocat-ATC DCL function ==> EAST ATMB to provide DCL Interface [TAL_FF]: Refer to SDR MoM Item #78, Interfaces available in Tower. DCL will be in PD and HQ TWRs. Action is closed. | 2016-05-16 | 2016-05-16 | 2016-07-29 | Closed |  |  | EAST ATMB
TM Action |  | SHH-5 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | SSR code allocation improvment – RFT Clause 3.2.6.3.2.6 & 3.4.5.1.7.4 | MoM Reference 3.3 Thales: Not part of the current proposal from Thales. Pending Agreed Resolution: This ECR will be implemented in the frame of Shanghai TMA project. High level description: Thales proposes to implement a Callsign highlight in the case of a coupled track with a mismatch Callsign, i.e. the Callsign in the Flight Data Record of that track does not match the received Callsign in the downlink ModeS message. Thales confirms that the Callsign highlight in the case of a SSR code mismatch function will be kept (as current NEHUP baseline). | 2015-12-23 | 2015-12-23 | 2016-02-10 | Closed | ECR_STMA_14 - Callsign Mismatch released in ECR batch #4. |  | Thales - TAL
TM Action |  | SHH-4 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | External Interfaces Summary Table - No specific RFT clause | MoM Reference 2.12 Thales will provide External Interfaces Summary Table in the Technical Description | 2015-05-08 | 2015-05-08 | 2015-07-10 | Closed | Refer Contract Annex 4 System Technical Description (Section 2.2) |  | Thales - TAL
TM Action |  | SHH-3 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | AODB Interface - RFT clause 3.13.14.1 | MoM Reference 2.8 Thales will correct the Architecture Drawing to show the AODB over IP as an interface for Eurocat-TWR | 2015-05-08 | 2015-05-08 | 2015-07-10 | Closed | Refer Contract Annex 4 System Technical Description RevA (Fig 3 Pudong TWR & Fig 4 Hongqiao TWR) |  | Thales - TAL
TM Action |  | SHH-2 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | EFEED Interface - RTF clause 2.2.1.9 | MoM Reference 2.6 Thales states that EFEED information (data dictionary) will be provided before end of June 2015 through the NEHUP contract | 2015-05-08 | 2015-05-08 | 2015-07-22 | Closed | Delivered under NEUP. 22 July 2015 |  | Thales - TAL
TM Action |  | SHH-1 | MoM_Shanghai_TMA_Contract_Nego_Rev_B | D-ATIS Interface | D-ATIS Interface Contract Neg_2.14 Thales: this interface was not listed in the RFT Agreed Resolution: East ATMB shall collect and assemble AWOS and D-ATIS information together to be sent to the Eurocat-TWR system using the planned AWOS Serial interface. Thales shall propose a format for this interface in order to finalise the interface design. Thales confirms that the D-ATIS version letter (when received) will then be displayed in the DCL window. | 2016-02-22 | 2016-02-22 | 2016-02-10 | Closed | ECR_TWR_6 - D-ATIS Interface released. Please note ECR_TWR_6 is merged with ECR_TWR_2 - AWOS Interface (SMF-SHA-002). |  | Thales - TR6
Generated at Mon Feb 27 15:27:43 AEDT 2017 by Ferrier, Fay using JIRA 6.4.13#64028-sha1:b7939e92b94c2a010d1b76f65a990594814da139.